## Sheet1
Project Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Hours used | 30 | 30 | 30 | 30 | 30 | 30 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
Task
Project Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Preparation Phase
Project Management - General
-Alex | 1 | 1
Create Project Plan
-Alex | 3
Set up Communication Tools
-Alex | 1
-Brandon | 1
-Emily | 1
-Natalie | 1
-Shane | 1
Idea development
-Brandon | 4 | 1
-Emily | 4 | 1
-Natalie | 4 | 1
-Shane | 4 | 1
Team meetings and review
-Alex | 1 | 1
-Brandon | 1 | 1
-Emily | 1 | 1
-Natalie | 1 | 1
-Shane | 1 | 1
Document ideas and motivations
-Alex |  | 1
-Brandon |  | 3
-Emily |  | 2
-Natalie |  | 2
-Shane |  | 2
Refine scope for initial project
-Alex |  | 1
-Brandon |  | 2
-Emily |  | 3
-Natalie |  | 2
-Shane |  | 2
Project Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Planning Phase
Project Management - General
-Alex |  |  | 1 | 1 | 1
Define goals and aims of project
-Alex |  |  | 2
-Brandon |  |  | 2
-Emily |  |  | 2
-Natalie |  |  | 2
-Shane |  |  | 2
Team meetings and review
-Alex |  |  | 2 | 2 | 1
-Brandon |  |  | 2 | 2 | 1
-Emily |  |  | 2 | 2 | 1
-Natalie |  |  | 2 | 2 | 1
-Shane |  |  | 2 | 2 | 1
High level project plan
-Alex |  |  | 2 | 4
Research existing landscape
-Shane |  |  | 2 | 3
-Emily |  |  | 2 | 4
Research potential tools
-Brandon |  |  |  | 4
-Natalie |  |  | 3 | 4
Research skills required
-Shane |  |  |  |  | 4
-Natalie |  |  |  |  | 4
Document sucess criteria from aims
-Alex |  |  |  |  | 3
Risk assessment
-Brandon |  |  |  |  | 4
Project Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Detailed Design Phase
Project Management - General
-Alex | [5 empty] | 1 | 1 | 1 | 1
Team meetings and review
-Alex | [5 empty] | 1 | 2 | 2 | 2
-Brandon | [5 empty] | 1 | 2 | 2 | 2
-Emily | [5 empty] | 1 | 2 | 2 | 2
-Natalie | [5 empty] | 1 | 2 | 2 | 2
-Shane | [5 empty] | 1 | 2 | 2 | 2
Initial UX design
-Brandon | [5 empty] | 2 | 8
-Emily | [5 empty] | 2 | 8
Develop Testing Criteria
-Shane |  |  |  |  | 2
-Emily |  |  |  |  | 2
A3 Report
-Alex |  |  |  |  | 1 | 4
-Brandon |  |  |  |  | 1 | 4
-Emily |  |  |  |  | 1 | 4
-Natalie |  |  |  |  | 1 | 4
-Shane |  |  |  |  | 1 | 4
Develop Functional Testing plan
-Brandon | [6 empty] | 6
-Natalie | [6 empty] | 14
Data Structure Design
-Emily | [6 empty] | 6
-Alex | [6 empty] | 13
-Shane | [6 empty] | 14
Initial Website UX Prototype
-Brandon | [7 empty] | 14 | 14
-Natalie | [7 empty] | 14 | 14
Setup Hosting Environment
-Shane | [7 empty] | 14
Setup External Access (DNS etc)
-Alex | [7 empty] | 13
Search Service Design
-Emily | [7 empty] | 14
Web Services Detailed Design
-Alex | [8 empty] | 13
-Shane | [8 empty] | 14
-Emily | [8 empty] | 14
Project Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Implementation Phase
Project Management - General
-Alex | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1
Team meetings and review
-Alex | [9 empty] | 2 | 2 | 2 | 2 | 2 | 2
-Brandon | [9 empty] | 2 | 2 | 2 | 2 | 2 | 2
-Emily | [9 empty] | 2 | 2 | 2 | 2 | 2 | 2
-Natalie | [9 empty] | 2 | 2 | 2 | 2 | 2 | 2
-Shane | [9 empty] | 2 | 2 | 2 | 2 | 2 | 2
Database Deployment
-Natalie | [9 empty] | 14 | 14 | 14
-Shane | [9 empty] | 14 | 14 | 14
Database Testing and Bugfix
-Natalie | [12 empty] | 8 | 8
-Shane | [12 empty] | 8 | 8
Website Deployment
-Brandon | [9 empty] | 14 | 14 | 14
-Emily | [9 empty] | 14 | 14 | 14
Website Testing and Bugfix
-Alex | [12 empty] | 8
-Brandon | [12 empty] | 14 | 14
-Emily | [12 empty] | 14
-Natalie | [12 empty] | 6 | 6
-Shane | [12 empty] | 6 | 6
User Acceptance Testing
-Alex | [13 empty] | 13
-Emily | [13 empty] | 14
Creating Marketing Strategy
-Alex | [9 empty] | 13 | 13
Implement SEO
-Alex | [11 empty] | 13 | 5
Website Go Live
-Alex | [14 empty] | 13
-Brandon | [14 empty] | 14
-Shane | [14 empty] | 14
Project Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Documentation and Review Phase
Project Management - General
-Alex | [15 empty] | 2
Project Close
-Alex | [15 empty] | 6
Team meetings and review
-Alex | [15 empty] | 2
-Brandon | [15 empty] | 2
-Emily | [15 empty] | 2
-Natalie | [15 empty] | 2
-Shane | [15 empty] | 2
Document Test Results
-Shane | [15 empty] | 14
Update documentation
-Brandon | [15 empty] | 14
-Alex | [15 empty] | 6
Create user Guides
-Natalie | [14 empty] | 14 | 14
-Emily | [14 empty] | 14 | 14